## Sheet1
1 | Initial Planning | Hours | Milestones | Key Decisions
1.1 | Brain Storming Project Design | 3
1.2 | Determine Order of Processes | 1
1.3 | Outline Possible components | 1 |  | Cost, availability
1.4 | Decide on Solution | 2
1.5 | Break Down System Parts | 1
1.6 | Assign responsibilities | 1
2 | Renewable Energy Components
2.01 | design pv array/system | 2 |  | # of panels
2.02 | design wind system | 2 |  | Use of dummy load
2.03 | design battery storage | 2 |  | # of batteries in series/paralell
2.04 | choose current sensor | 1
2.05 | choose voltage sensor | 1
2.06 | build pv array | 4 | pv array charges batteries
2.07 | assemble wind turbine | 3 | wind turbine charges batteries
2.08 | wire batteries | 1 | batteries ready for RE sources
2.09 | set up annomometer for wind data (roof of green) | 2 | collect 1 week of wind data
2.1 | write energy modeling equations |  | used to compare against model
3 | Load Controller
3.1 | gather load data | 2 |  | fie type/size
3.2 | create load data file | 1
3.3 | choose controller | 1 |  | easy of data writing/reading
3.4 | choose load | 3 |  | size of load, AC or DC
3.5 | write software | 5 | reading data from text file on flash drive
3.6 | debug/test software | 5 | bug free software
3.7 | design circuitry for load | 4
3.8 | mesh with load for project | 2 | data file drives a load
4 | Energy Controler
4.1 | research types of controllers | 2
4.2 | choose controller | 1
4.3 | determine which sensors required | 1
4.4 | write logic | 5
4.5 | wire components | 2
4.6 | create GUI | 2 | graphical interface for monitoring
4.7 | debug/test
5 | Website design
5.01 | initial setup | 2 |  | Follow assigned template
5.02 | create pages | 2
5.03 | add content | 1
5.04 | update content | 0.5
6 | System Assembly
7.1 | review subsystem layout | 1
7.2 | combine subsystems | 5
7.3 | test full system | 4
| Detention Layout | 2